Team 37:

Models we have decided on:

- Ridge regression as first step baseline - done

- Lasso/ ElasticNet as baseline – not started

- Random Forest – in fine-tuning

- XGBoost – in fine-tuning + spatial feature comparison

- MLP

- GNN as most advanced model

Who is doing what

Emily – completed Ridge Regression, working on XGBoost

Shreya – working on Random Forest

Vaishnavi – working on GNN and MLP

Priya - ?

Pallavi - ?

- I suggest that Priya and Pallavi help Vaishnavi work on GNN and MLP because they are time intensive to train and more people working on it will speed things up

Workflow – what everyone should be doing

- Run the preprocessing function (on github) on rna and protein data

- You will get an output that you should use for all models (rna_data, protein_data, and rna_hvg files)

- Run a cross-validation run of your model using the cv_splits.json file (on github)

  - This splits the data into 5 folds so your model runs 5 times – you should then have 5 pearson r, r2, RMSE values to compare and understand your model performance

  - Upload your results on github

- Once we have cross validation results from all models, we can understand which models are performing well

- Tree-based models and baselines are also worth comparing with spatial features incorporated vs without to see if performance improves

Some points on the feedback from the presentation feedback email:

- Everyone needs to use the preprocessing and cross-validation steps that I have put on github otherwise we can’t compare results

- I have updated the cross-validation split file to be spatially aware – previously this could have been inflating results as the split was allowing for data leakage between train/test bins

- We need to have regular meetings to keep each other up to date – we should make a clear outline of our progress, workload split and timeline for the rest of the project